## Slide 1
Entitlement Pipeline
16 active projects · 7 municipalities
Fri, Oct 30, 2026

## Slide 2
0
Prospect
0
LOI
6
Diligence
0
Development
10
OYL
Project | Municipality | Stage | Acres | P&Z hearing | Council | Flags
Chateau Valley | Wildwood | Diligence | — | Mon, Dec 7, 2026 (if filed now) | Mon, Dec 14, 2026 | 
Cottleville Springs | Cottleville | Diligence | — | Mon, Dec 7, 2026 (if filed now) | Wed, Dec 16, 2026 | 
Mia Bella | Wildwood | Diligence | — | Mon, Dec 7, 2026 (if filed now) | Mon, Dec 14, 2026 | 
Sagebrook | Dardenne Prairie | Diligence | — | Wed, Dec 9, 2026 (if filed now) | Wed, Dec 16, 2026 | 
Towers Rd Lots | St. Charles County (Unincorporated) | Diligence | — | Wed, Dec 16, 2026 (if filed now) | Mon, Jan 11, 2027 | 
Weldon Reserve | Dardenne Prairie | Diligence | — | Wed, Dec 9, 2026 (if filed now) | Wed, Dec 16, 2026 | 
107 Lock Dr | Ballwin | OYL | — | — | — | 
11615 Serama | Des Peres | OYL | — | — | — | 
1400 Bopp Rd | Des Peres | OYL | — | — | — | Diligence ending
1421 and 1435 Schoettler Rd | Chesterfield | OYL | — | Mon, Dec 14, 2026 (if filed now) | — | Diligence ending
247 Geremma | Ballwin | OYL | — | — | — | 
3701 Bear Tooth | Wildwood | OYL | — | Mon, Dec 7, 2026 (if filed now) | Mon, Dec 14, 2026 | Diligence ending
413 Ries Rd | Ballwin | OYL | — | — | — | 
701 Joyce Ann | Ballwin | OYL | — | — | — | 

## Slide 3
Project | Municipality | Stage | Acres | P&Z hearing | Council | Flags
802 Connie Ln | Ballwin | OYL | — | — | — | 
9 Wildwood Point | Wildwood | OYL | — | Mon, Dec 7, 2026 (if filed now) | Mon, Dec 14, 2026 | 

## Slide 4
Chateau Valley
Diligence · Wildwood
Key facts
Address | —
Acreage | —
Zoning | —
Case number(s) | —
Application filed | Not yet
Diligence expires | —
Closing | —
Timeline if filed today
Fri, Oct 30, 2026 Submit application (est.) · no published deadline; assumes 30 days before P&Z
Mon, Dec 7, 2026 P&Z hearing
Mon, Dec 14, 2026 Council / Board vote
Next steps
No open tasks.

## Slide 5
Cottleville Springs
Diligence · Cottleville
Key facts
Address | —
Acreage | —
Zoning | —
Case number(s) | —
Application filed | Not yet
Diligence expires | —
Closing | —
Timeline if filed today
Mon, Nov 9, 2026 Submittal deadline
Mon, Dec 7, 2026 P&Z hearing
Wed, Dec 16, 2026 Council / Board vote
Next steps
No open tasks.

## Slide 6
Mia Bella
Diligence · Wildwood
Key facts
Address | —
Acreage | —
Zoning | —
Case number(s) | —
Application filed | Not yet
Diligence expires | —
Closing | —
Timeline if filed today
Fri, Oct 30, 2026 Submit application (est.) · no published deadline; assumes 30 days before P&Z
Mon, Dec 7, 2026 P&Z hearing
Mon, Dec 14, 2026 Council / Board vote
Next steps
No open tasks.

## Slide 7
Sagebrook
Diligence · Dardenne Prairie
Key facts
Address | 1670 Stump Rd and 7393 Highway N
Acreage | —
Zoning | —
Case number(s) | —
Application filed | Not yet
Diligence expires | —
Closing | —
Timeline if filed today
Fri, Oct 30, 2026 Submit application (est.) · no published deadline; assumes 30 days before P&Z
Wed, Dec 9, 2026 P&Z hearing (est.)
Wed, Dec 16, 2026 Council / Board vote (est.)
Next steps
Check to see if we can do a double reading
Latest note
Passed Zoning with P&Z, Should be on next Council Agenda 10/21
— Unknown, Thu, Oct 15, 2026

## Slide 8
Towers Rd Lots
Diligence · St. Charles County (Unincorporated)
Key facts
Address | 4033 Towers Rd, Saint Charles MO
Acreage | —
Zoning | —
Case number(s) | —
Application filed | Not yet
Diligence expires | Fri, Dec 4, 2026
Closing | Wed, Dec 30, 2026
Timeline if filed today
Fri, Nov 20, 2026 Submittal deadline (est.)
Wed, Dec 16, 2026 P&Z hearing (est.)
Mon, Dec 21, 2026 Council / Board first reading
Mon, Jan 11, 2027 Council / Board final vote (est.)
Next steps
No open tasks.

## Slide 9
Weldon Reserve
Diligence · Dardenne Prairie
Key facts
Address | —
Acreage | —
Zoning | —
Case number(s) | —
Application filed | Not yet
Diligence expires | —
Closing | —
Timeline if filed today
Fri, Oct 30, 2026 Submit application (est.) · no published deadline; assumes 30 days before P&Z
Wed, Dec 9, 2026 P&Z hearing (est.)
Wed, Dec 16, 2026 Council / Board vote (est.)
Next steps
No open tasks.

## Slide 10
107 Lock Dr
OYL · Ballwin
Key facts
Address | 107 Lock Dr
Acreage | —
Zoning | —
Case number(s) | —
Application filed | Not yet
Diligence expires | —
Closing | Thu, Jul 30, 2026
Timeline if filed today
Fri, Oct 30, 2026 Submit application (est.) · no published deadline; assumes 30 days before P&Z
— P&Z hearing · no upcoming P&Z meetings loaded for this city
Next steps
No open tasks.

## Slide 11
11615 Serama
OYL · Des Peres
Key facts
Address | 11615 Serama
Acreage | —
Zoning | —
Case number(s) | —
Application filed | Not yet
Diligence expires | —
Closing | Wed, Sep 9, 2026
Timeline if filed today
Fri, Oct 30, 2026 Submit application (est.) · no published deadline; assumes 30 days before P&Z
— P&Z hearing · no upcoming P&Z meetings loaded for this city
Next steps
No open tasks.

## Slide 12
1400 Bopp Rd
OYL · Des Peres
Key facts
Address | 1400 Bopp Rd, Des peres, MO
Acreage | —
Zoning | —
Case number(s) | —
Application filed | Not yet
Diligence expires | Fri, Oct 30, 2026
Closing | Tue, Dec 15, 2026
Timeline if filed today
Fri, Oct 30, 2026 Submit application (est.) · no published deadline; assumes 30 days before P&Z
— P&Z hearing · no upcoming P&Z meetings loaded for this city
Next steps
No open tasks.

## Slide 13
1421 and 1435 Schoettler Rd
OYL · Chesterfield
Key facts
Address | 1421 & 1435 Schoettler Rd
Acreage | —
Zoning | —
Case number(s) | —
Application filed | Not yet
Diligence expires | Tue, Nov 24, 2026
Closing | Tue, Dec 1, 2026
Timeline if filed today
Fri, Oct 30, 2026 Submit application (est.) · no published deadline; assumes 30 days before P&Z
Mon, Dec 14, 2026 P&Z hearing
— Council / Board vote · past the loaded schedule
Next steps
No open tasks.
Latest note
Offer sent
— Unknown, Thu, Oct 15, 2026

## Slide 14
247 Geremma
OYL · Ballwin
Key facts
Address | 247 Geremma
Acreage | —
Zoning | —
Case number(s) | —
Application filed | Not yet
Diligence expires | —
Closing | Tue, Sep 29, 2026
Timeline if filed today
Fri, Oct 30, 2026 Submit application (est.) · no published deadline; assumes 30 days before P&Z
— P&Z hearing · no upcoming P&Z meetings loaded for this city
Next steps
No open tasks.

## Slide 15
3701 Bear Tooth
OYL · Wildwood
Key facts
Address | 3701 Bear Tooth Lane
Acreage | —
Zoning | —
Case number(s) | —
Application filed | Not yet
Diligence expires | Wed, Nov 18, 2026
Closing | Tue, Dec 1, 2026
Timeline if filed today
Fri, Oct 30, 2026 Submit application (est.) · no published deadline; assumes 30 days before P&Z
Mon, Dec 7, 2026 P&Z hearing
Mon, Dec 14, 2026 Council / Board vote
Next steps
No open tasks.
Latest note
Offer sent
— Unknown, Fri, Oct 16, 2026

## Slide 16
413 Ries Rd
OYL · Ballwin
Key facts
Address | 413 Ries Rd
Acreage | —
Zoning | —
Case number(s) | —
Application filed | Not yet
Diligence expires | —
Closing | Fri, Oct 9, 2026
Timeline if filed today
Fri, Oct 30, 2026 Submit application (est.) · no published deadline; assumes 30 days before P&Z
— P&Z hearing · no upcoming P&Z meetings loaded for this city
Next steps
No open tasks.

## Slide 17
701 Joyce Ann
OYL · Ballwin
Key facts
Address | 701 Joyce Ann
Acreage | —
Zoning | —
Case number(s) | —
Application filed | Not yet
Diligence expires | —
Closing | Fri, Sep 4, 2026
Timeline if filed today
Fri, Oct 30, 2026 Submit application (est.) · no published deadline; assumes 30 days before P&Z
— P&Z hearing · no upcoming P&Z meetings loaded for this city
Next steps
No open tasks.

## Slide 18
802 Connie Ln
OYL · Ballwin
Key facts
Address | 802 Connie Ln
Acreage | —
Zoning | —
Case number(s) | —
Application filed | Not yet
Diligence expires | —
Closing | Wed, Jul 29, 2026
Timeline if filed today
Fri, Oct 30, 2026 Submit application (est.) · no published deadline; assumes 30 days before P&Z
— P&Z hearing · no upcoming P&Z meetings loaded for this city
Next steps
No open tasks.

## Slide 19
9 Wildwood Point
OYL · Wildwood
Key facts
Address | 9 Wildwood Point
Acreage | —
Zoning | —
Case number(s) | —
Application filed | Not yet
Diligence expires | —
Closing | Fri, May 1, 2026
Timeline if filed today
Fri, Oct 30, 2026 Submit application (est.) · no published deadline; assumes 30 days before P&Z
Mon, Dec 7, 2026 P&Z hearing
Mon, Dec 14, 2026 Council / Board vote
Next steps
No open tasks.

## Slide 20
Date | Municipality | Meeting | Projects there
Mon, Nov 2, 2026 | Cottleville | P&Z | Cottleville Springs
Mon, Nov 2, 2026 | Wildwood | P&Z | Chateau Valley, Mia Bella, 3701 Bear Tooth, 9 Wildwood Point
Mon, Nov 2, 2026 | Chesterfield | Council / Aldermen | 1421 and 1435 Schoettler Rd
Wed, Nov 4, 2026 (projected) | Dardenne Prairie | Council / Aldermen | Sagebrook, Weldon Reserve
Mon, Nov 9, 2026 | Ballwin | Council / Aldermen | 107 Lock Dr, 247 Geremma, 413 Ries Rd, 701 Joyce Ann, 802 Connie Ln
Mon, Nov 9, 2026 | Wildwood | Council / Aldermen | Chateau Valley, Mia Bella, 3701 Bear Tooth, 9 Wildwood Point
Mon, Nov 9, 2026 | St. Charles County (Unincorporated) | Council / Aldermen | Towers Rd Lots
Mon, Nov 9, 2026 | Chesterfield | P&Z | 1421 and 1435 Schoettler Rd
Mon, Nov 9, 2026 | Cottleville | Submittal deadline | Cottleville Springs
Wed, Nov 11, 2026 (projected) | Dardenne Prairie | P&Z | Sagebrook, Weldon Reserve
Mon, Nov 16, 2026 | Chesterfield | Council / Aldermen | 1421 and 1435 Schoettler Rd
Wed, Nov 18, 2026 | Cottleville | Council / Aldermen | Cottleville Springs
Wed, Nov 18, 2026 (projected) | Dardenne Prairie | Council / Aldermen | Sagebrook, Weldon Reserve
Wed, Nov 18, 2026 (projected) | St. Charles County (Unincorporated) | P&Z | Towers Rd Lots
Fri, Nov 20, 2026 (projected) | St. Charles County (Unincorporated) | Submittal deadline | Towers Rd Lots
Mon, Nov 23, 2026 | Ballwin | Council / Aldermen | 107 Lock Dr, 247 Geremma, 413 Ries Rd, 701 Joyce Ann, 802 Connie Ln
Mon, Nov 23, 2026 | Chesterfield | P&Z | 1421 and 1435 Schoettler Rd
Mon, Nov 23, 2026 | St. Charles County (Unincorporated) | Council / Aldermen | Towers Rd Lots